## week2
Computer Science 2 Project | Team Members: | MARQUEZ
Group Progress Report |  | DUROY
4TH Quarter |  | COSTO
MORGA
Week 1-2 ( March 2-13 )
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
1. Continue debugging and fixing the core | 1. Initial debugging results and identified | 1. Improvements made to taskoverview and
features. | errors in the program | grade calculator feature
2. Enhance UI and program display | 2. Issues found in task overview and | 2. Started debugging and testing the
3. Prepare the implementation of CRUD | grade calculator feature | program
requirements | 3. Observations in early testing | 3. Initial tweaks were made in the code
| performance. | for better performance.
STRENGTH
We, as a group, can work under pressure and thankfully can still produce results. We are persistent in debugging and
improving our program. Lastly, we continuously progress despite time constraints, misunderstandings, and challenges between
members.
AREAS FOR DEVELOPMENT
Delayed responses causing the team to fall behind schedule
Limited time available for development (time constraints)
Some members were not cooperative or unavailable during critical work periods
STRATEGY FOR SUCCESS
Continued debugging despite delays
Focused on improving key features (grade calculator and task overview)
Ongoing adjustments to meet CRUD requirements
Worked under pressure to maintain progress

## week1
Computer Science 2 Project | Team Members: | MARQUEZ
Group Progress Report |  | DUROY
4TH Quarter |  | COSTO
MORGA
Week 3-4 ( March 16-27 )
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
1. COMPLETE CRUD FEATURES | 1 Additional debugging results | 1. Continued Debugging and testing
2. FINALIZE ALL FEATURE | 2 Feedback for program (03.01) | 2. More tweaks and improvement of
FUNCTIONALITIES | 3 incomplete CRUD functionalities | overall program
3. REDUCE ERRORS |  | 3. Program reached an approximate
4. ACHIEVE 100% PROJECT |  | 80% functionality
COMPLETION
STRENGTH
We, as a group, can work under pressure and thankfully can still produce results. We are persistent in debugging and
improving our program. Lastly, we continuously progress despite time constraints, misunderstandings, and challenges between
members.
AREAS FOR DEVELOPMENT
Ongoing delays and time constraints Lack of cooperation from some members during critical times
STRATEGY FOR SUCCESS
Continued development and debugging
Focused on completing major system requirements (CRUD)
Maintained progress despite team and time challenges

## week3
Computer Science 2 Project | Team Members: | MARQUEZ
Group Progress Report |  | DUROY
4TH Quarter |  | COSTO
MORGA
Week 5-6 ( March 30, 31 )
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week4
Computer Science 2 Project | Team Members: | MARQUEZ
Group Progress Report |  | DUROY
4TH Quarter |  | COSTO
MORGA
Week 7 (April 6-7)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
write at least 2 task
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS